## Sheet1
Work Item Type | Title | State | Estimate
Epic | Mobile Field Research App | New
User Story | Record wildlife observations | New | 5
Task | Implement observation entry UI | New | 3
Task | Implement geolocation capture | New | 3
Epic | IoT Device Integration | New
User Story | Ingest telemetry from GPS collars | New | 8
Task | Implement telemetry ingestion pipeline | New | 5
Task | Implement device authentication | New | 3
Epic | Real-time Tracking & Alerts | New
User Story | Generate movement alerts | New | 5
Task | Implement alert rules engine | New | 3
Task | Implement restricted zone detection | New | 3
Epic | Reporting & Heatmaps | New
User Story | Visualize animal movement heatmaps | New | 8
Task | Implement heatmap rendering | New | 5
Task | Optimize queries for <500ms | New | 3
Epic | Offline Sync | New
User Story | Sync offline data | New | 5
Task | Implement offline storage | New | 3
Task | Implement sync mechanism | New | 3